## Sheet1
Name | Description | Likelihood | Impact | Mitigation | Response | Category = risk category to group risks
Initial plan mistake | This could be due to a lack of understanding the project scope or not giving myself enough time to do certain tasks | Low | Medium | Allocate dedicated time to planning. | Review and reformulate the plan. | Name = describes the risk
Product does not meet minimum viable product (MVP) requirements | Failed to meet some of the requirements set out in the project specification. This could be not having a working application at the end or not keeping the trello board up to date with my progress and user stories or not providing one of the deliverables. | Low | High | This links back to the planning stage. A good plan should help to avoid this risk by allocating the right amount of time to each element of the project and making sure all elements are accounted for. | Don't start working on any extra bits before getting the basic functionality working how it should.
Poor risk management | Not properly managing risks and planning mitigations and responses to these risks could lead to not meeting the MVP of the project. | Low | High | Properly document all risks in a risk register with mitigation strategies and responses. | Review risks and update if new ones are identified throughout the project
Poor Communication | Poor communication with the client or consultant project liason could leead to the deliverable not meeting the requirements and also could create other problems. | Medium | Medium | Communication will mostly be with the client in this project, due to it being an individual project. This communication will need to be prompt due to the client being busy with their own work. The fact that we are remote working also needs to be taken into account since this could delay responses. Communication must also be kept clear, concise and professional. | Ensure that questions are asked in plenty of time before the deadline and professional standards.
Internet connection issues | Only point this should be a major issue is when doing the presentation | Low | Low | Make sure that any work on online sites is saved to my device so that I can continue working on it. | If issues occur and are persistent, especially on presentation day, contact the operations team ASAP. | RBS ID = Risk Beakdown Structure ID number
Illness | Any illness or ailment that could affect my ability to continue working on the project eg Covid-19 | Low | Low | Make sure to keep healthy by getting enough sleep, exercising and eating healthily. | Let someone in QA know ASAP if I do fall ill and cannot work. | Probabilty (or likelihood) = of its occurrence rated on an integer scale | 0-1 scale
Data breach due to being attacked by hackers | Sensitive infoformation, such as users' personal details and login details for emails, could be exposed to the hackers. | Low | High | Ensure any sensitive info is only accessed when needed and securely stored. | If login information for emails has potentially been hacked, change details immediately. | mitigation = common steps within IT projects are Identify, Analyze, Plan, Response, Monitor and Control
Insufficient testing | Insufficient testing could result in bugs or bad code going unnoticed which could pose a risk to the reliability and security of the final product. | Medium | High | Implement the test driven development principal to ensure that code is being tested throughout the project and not just at the end. Make sure it tests all business cases outlined in the scope. | Ensure that as much of the automation as possible is tested and that any potential bugs are dealt with.
Loss of data | Loss of data due to accidental deletion or the hard drive being corrupt or some other reason is always a possibility in these types of projects. | Low | High | Make frequent backups and have a good version control system in place (eg GitHub). | If data is lost and cannot be retrieved then the project would need to be built up from the beginning again. So it is better to avoid this possibility as much as possible by making regular backups and keeping the GitHub repository updated. | Risk Score (or risk rating) = multiplication of probability and impact and is often used to rank risks
Sensitive customer data | Any real customer data needs to be handled appropriately and stored securely as this poses a potential GDPR risk. | High | High | For the purposes or this project, fake customer data will be used, generated from the bestrandoms website and so the risk is reduced. However, security will still be considered when building the automation and implemented wherever possible. | Store any user details securely and use fake data within the project.
risk register is qualitative if ranking used is high to low impact
quantitative if numerical ranking eg $1m impact and 50% probability